## ProjectSchedule
Senior Deisgn Project 2
[Company Name]
Jermey Astle & Chris Ruby | Project Start: | 2018-08-29
| Display Week: | 1 |  |  | 2018-08-27 | [6 empty] | 2018-09-03 | [6 empty] | 2018-09-10 | [6 empty] | 2018-09-17 | [6 empty] | 2018-09-24 | [6 empty] | 2018-10-01 | [6 empty] | 2018-10-08 | [6 empty] | 2018-10-15
 | time axis 2018-08-27 to 2018-10-21
TASK |  | START | END | DAYS | time axis 2018-08-27 to 2018-10-21
Initial Simulation Results |  | 2018-08-30 | 2018-09-11 | 13 | 2018-08-30: Milestone
Researching |  | 2018-08-30 | 2018-09-05 | 7 | 2018-08-30: Task
Simulating |  | 2018-09-05 | 2018-09-11 | 7 | 2018-09-05: Task
Simulation Results |  | 2018-09-05 | 2018-09-11 | 7 | 2018-09-05: Deliverable
Task 4 |  | 2018-01-13 | 2018-01-18 | 6
Task 5 |  | 2018-01-06 | 2018-01-08 | 3
Completion of Layout |  | 2018-09-11 | 2018-09-17 | 7 | 2018-09-04: Milestone
Interpreting Simulation Results |  | 2018-09-11 | 2018-09-13 | 3 | 2018-09-11: Task
Designing |  | 2018-09-13 | 2018-09-17 | 5 | 2018-09-13: Task
Documents |  | 2018-09-11 | 2018-09-17 | 7 | 2018-09-11: Deliverable
Task 4 |  | 2018-01-15 | 2018-01-17 | 3
Task 5 |  | 2018-01-18 | 2018-01-21 | 4
Completion of Project |  | 2018-09-17 | 2018-10-28 | 42 | 2018-09-17: Milestone
Schmatics |  | 2018-09-17 | 2018-09-25 | 9 | 2018-09-17: Deliverable
Documenting |  | 2018-09-25 | 2018-09-27 | 3 | 2018-09-25: TASK
PCB Layout |  | 2018-09-27 | 2018-10-04 | 8 | 2018-09-27: Deliverables
Building |  | 2018-10-04 | 2018-10-09 | 6 | 2018-10-04: Task
Debugging |  | 2018-10-09 | 2018-10-12 | 4 | 2018-10-09: Task
Loaded Circuit Board |  | 2018-10-12 | 2018-10-15 | 4 | 2018-10-12: Deliverable
Testing |  | 2018-10-15 | 2018-10-22 | 8 | 2018-10-15: Task
Final Report |  |  | 2018-10-28
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.